## Sheet1
TicketID | TicketType | Priority | Status | Assigned to | Created Date | Completed Date | Estimated Hours | Actual Hours | Comments
T001 | Bug | High | Completed | Anusha | 2025-01-02 | 2025-01-03 | 5 | 6 | Fixed login issue
T002 | Task | Medium | Completed | Kiran | 2025-01-02 | 2025-01-04 | 4 | 4 | Added new buttons
T003 | Enhancement | Low | In Progress | Varun | 2025-01-03 |  | 6 |  | UI redesign ongoing
T004 | Bug | High | Open | Priya | 2025-01-04 |  | 3 |  | Crash on submit page
T005 | Task | Medium | Completed | Mahesh | 2025-01-04 | 2025-01-05 | 2 | 3 | Updated fields
T006 | Task | High | In Progress | Sruthi | 2025-01-05 |  | 5 |  | Backend logic will change
T007 | Enhancement | Low | Completed | Naveen | 2025-01-05 | 2025-01-06 | 3 | 3 | Dashboard color change
T008 | Bug | High | Open | Kavya | 2025-01-06 |  | 4 |  | API returning 500
T009 | Task | Medium | Completed | Rohit | 2025-01-06 | 2025-01-07 | 2 | 2 | Reports added
T010 | Enhancement | Low | Completed | Divya | 2025-01-07 | 2025-01-08 | 5 | 4 | Improved performance
T011 | Bug | High | In Progress | Anusha | 2025-01-08 |  | 4 |  | Issue in file upload
T012 | Task | Medium | Completed | Kiran | 2025-01-08 | 2025-01-09 | 3 | 3 | Mobile view changes
T013 | Bug | High | Completed | Priya | 2025-01-09 | 2025-01-10 | 6 | 7 | Security patch fixed
T014 | Task | Medium | Open | Varun | 2025-01-10 |  | 4 |  | Pending review
T015 | Enhancement | Low | Completed | Kavya | 2025-01-10 | 2025-01-11 | 3 | 2 | Icon updates done
T016 | Task | Medium | In Progress | Divya | 2025-01-11 |  | 4 |  | Working on document upload
T017 | Bug | High | Open | SRuthi | 2025-01-12 |  | 3 |  | Session timeout issue
T018 | Task | Medium | Completed | Naveen | 2025-01-12 | 2025-01-13 | 2 | 2 | Form validations
T019 | Enhancement | Low | Completed | Rohit | 2025-01-13 | 2025-01-14 | 4 | 4 | Added animations
T020 | Bug | High | Completed | Varun | 2025-01-13 | 2025-01-14 | 5 | 5 | Memory leak issue
T021 | Task | Medium | In Progress | Anusha | 2025-01-14 |  | 3 |  | Modified search filter
T022 | Enhancement | Low | Completed | Kiran | 2025-01-14 | 2025-01-15 | 5 | 6 | Updated layouts
T023 | Bug | High | Open | Priya | 2025-01-15 |  | 6 |  | Intermittent network issue
T024 | Task | Medium | Completed | Mahesh | 2025-01-15 | 2025-01-16 | 2 | 2 | Menu redesign
T025 | Bug | High | Completed | Divya | 2025-01-16 | 2025-01-17 | 4 | 5 | Resolved billing error
T026 | Enhancement | Low | In Progress | Kavya | 2025-01-16 |  | 5 |  | Homepage improvements
T027 | Task | Medium | Open | Naveen | 2025-01-16 |  | 3 |  | To be reviewed
T028 | Bug | High | Completed | Rohit | 2025-01-17 | 2025-01-18 | 4 | 4 | Fixed upload hang issue
T029 | Task | Medium | Completed | Sruthi | 2025-01-17 | 2025-01-18 | 3 | 3 | Email trigger fixed
T030 | Enhancement | Low | Completed | Mahesh | 2025-01-18 | 2025-01-19 | 4 | 4 | Crash on submit page